## Agile_Estimates
	Requirements	Value Points	User Story Points	BFTB

7.0 Synchronize	Synchronize app to calendar	5	21	0.238095238		7.0 Synchronize	Synchronize app to calendar	5	21	0.238095238
7.0 Synchronize	Synchronize app to address book	5	21	0.238095238		7.0 Synchronize	Synchronize app to address book	5	21	0.238095238
1.0 Record of Event	Creating an Event	5	1	5
1.0 Record of Event	Deleting an Event	5	1	5		1.0 Record of Event	Creating an Event	5	1	5
4.0 View Event	View the Event	5	1	5
1.0 Record of Event	Editing an Event	5	2	2.5
3.0 Profile	Attendee	5	13	0.384615385					Sprint 1
3.0 Profile	Walk-in	5	13	0.384615385					Sprint 2
2.0 Attendance Sheet	Setting-up the Attendance Sheet	5	5	1					Sprint 3
2.0 Attendance Sheet	Signing-up in the Attendance Sheet	5	5	1
5.0 Invitation	Attendee Confirmation	5	8	0.625
6.0 Print/Email Attendance Sheet	Emails the Attendance Sheet	5	8	0.625
6.0 Print/Email Attendance Sheet	Prints the Attendance Sheet	4	8	0.5
4.0 View Event	Sends Invitation	5	13	0.384615385
4.0 View Event	Receives Invitation	5	13	0.384615385